STUDENT PROJECT ROADMAP

Measuring Latent Drift in Multi-Turn LLM Conversations

16-week plan · Two-paper track · NYU Tandon

Bottom line 16 weeks, two deliverables. Paper A (short, 4–6 pages, submitted around Week 8–9) reports the first empirical measurement of NSP spectral-radius variation across LLM model families and conversation depths on public datasets. Paper B (full, 14–16 pages LNCS, submitted around Week 15–16) extends Paper A with a lightweight drift detector, a change-point analysis, and an evaluation showing the detector flags conversations that human annotators independently rate as drifted. Student profile: MS. Needs Python, pandas, matplotlib, basic statistics. Does NOT need HMM theory, EM derivations, or proofs. The theoretical understanding comes later if they continue into a PhD.

# 1. Project overview

The project answers one question that nobody has empirically tested: does the Neural-trace Semantic-state Process (NSP) — a continuous-state hidden Markov model for agent-trajectory drift — capture anything real in multi-turn LLM conversations? If it does, the spectral radius of the fitted dynamics matrix A should vary systematically across model families, conversation lengths, and task types. If it doesn’t, the NSP is a mathematical construct without empirical traction, and knowing that is equally valuable.

The project has two phases, each producing a paper:

| Phase | Weeks | Output | Contribution type |
| --- | --- | --- | --- |
| Phase 1: Measure | 1–9 | Paper A (short) | First empirical measurement of NSP drift signatures across models and datasets |
| Phase 2: Detect | 9–16 | Paper B (full) | Lightweight drift detector + human-annotation evaluation + change-point analysis |

What this feeds into This project is the pilot empirical study for the Math/Stats Narrative Drift proposal (P1). Every finding directly feeds into the larger research program: Spectral radius differs across models → Thread 2 power-law theorem (confirms drift rate varies, motivating the theory) NSP beats i.i.d. baseline → Thread 1 estimator suite (justifies the state-space model) Detector flags human-rated drift → Thread 2 change-point procedures (empirical anchor for the theoretical bounds) Any null result → Equally valuable — scopes where the framework applies and where it doesn’t

# 2. Datasets

Three public datasets, chosen for complementary properties. No data collection, no IRB, no API costs for the data itself.

| Dataset | Source | Size (sample) | Why it’s useful |
| --- | --- | --- | --- |
| LMSYS-Chat-1M | HuggingFace: lmsys/lmsys-chat-1m | 500–1,000 conversations | Real user–LLM conversations across GPT-4, Claude, Llama, Vicuna, etc. Model comparison. |
| ShareGPT | HuggingFace: anon8231489123/ShareGPT_Vicuna_unfiltered | 500–1,000 conversations | User-shared ChatGPT conversations of varying depth. Turn-depth analysis. |
| MT-Bench | HuggingFace: lmsys/mt_bench_human_judgments | 80 × 8 categories | Controlled multi-turn evaluation with known task categories and human quality scores. Ground-truth correlation. |

Data format requirement: all three must be converted to CSV with columns trajectory_id, turn_idx, text, and optionally reward. The conversion script is Week 1’s main deliverable. fit_nsp_text.py consumes this format directly.

# 3. Tools (all provided)

| Tool | What it does | Student’s job |
| --- | --- | --- |
| fit_nsp_text.py | Extracts features from text turns, fits NSP via EM, reports spectral radius of A + per-trajectory log-likelihood | Run it. Read the output. Don’t modify the EM internals. |
| run_exp_a.py | Validates the EM estimator on synthetic data (known ground truth) | Run it once to confirm the estimator works. Include the figure in Paper A’s appendix. |
| score_drift.py (new) | Takes fitted NSP params + new trajectories, computes per-trajectory drift scores | Will be built in Phase 2 (Week 9–10) with advisor help. |

# 4. Phase 1: Measure (Weeks 1–9)

Goal: run fit_nsp_text.py on all three datasets, collect spectral radii and log-likelihoods, analyze the results, and write Paper A.

## Week 1 — Setup and data acquisition

- Environment: Python 3.10+, venv, install numpy pandas tqdm scikit-learn matplotlib seaborn scipy.

- Download datasets from HuggingFace. LMSYS-Chat-1M is large (~1.5 GB); download the Parquet, filter to English, sample 1,000 conversations with ≥5 turns.

- Write three conversion scripts (one per dataset) that output CSV with trajectory_id, turn_idx, text. For LMSYS, also extract model_name as a metadata column.

- Deliverable: three clean CSVs in data/ folder. Quick sanity check: print turn-count histograms.

## Week 2 — Baseline runs

- Run fit_nsp_text.py on each CSV with default settings (handcrafted features, D=8, 40 EM iters). This is the first empirical look at the data.

- Collect spectral_radius_A, final_log_lik, per-trajectory log-likelihoods from each run.

- Run run_exp_a.py once with full parameters (N=[100,500,1000,2000], 10 seeds). Save the plot for Paper A’s appendix.

- Deliverable: nsp_output/ folders for each dataset. First look at spectral radii — do they differ?

## Week 3 — Per-model splits

- LMSYS-Chat-1M: split by model family (GPT-4, Claude, Llama, Vicuna, etc.). Run fit_nsp_text.py separately on each split.

- Collect spectral radii per model family. Compute Kruskal-Wallis H-test across model families.

- MT-Bench: split by task category (writing, roleplay, reasoning, math, coding, extraction, STEM, humanities). Run fit_nsp_text.py on each.

- Deliverable: Table 1 draft — spectral radius by model family. Table 2 draft — spectral radius by task category.

## Week 4 — Turn-depth analysis

- Stratify conversations by length: short (3–5 turns), medium (6–10), long (11–20), very long (20+).

- Run fit_nsp_text.py on each stratum. Record spectral radius per stratum.

- Compute Spearman ρ between conversation length and spectral radius across all trajectories.

- Deliverable: Figure 1 draft — spectral radius vs. conversation length (scatter + trend line).

## Week 5 — Baseline comparison

- Implement i.i.d. baseline: for each trajectory, compute log-likelihood under a simple i.i.d. Gaussian model (each turn’s features drawn independently from the corpus mean and variance). No EM, no state evolution.

- Implement AR(1) baseline: a single autoregressive coefficient (scalar ρ) fit per trajectory. Simpler than the full NSP but captures some temporal structure.

- Compare per-trajectory log-likelihoods: NSP vs. i.i.d. vs. AR(1). Paired Wilcoxon signed-rank test. Compute the fraction of trajectories where NSP wins.

- Deliverable: Table 3 draft — log-likelihood comparison. This is the key result: does the state-space model earn its complexity?

## Week 6 — Robustness checks

- Sensitivity to D: re-run with D=4, D=6, D=10, D=12. Does the spectral-radius ranking across models change?

- Sensitivity to feature extractor: if OpenAI API access is available, re-run with --features openai on a 200-conversation subset. Does the PCA-reduced embedding give a different ranking?

- Sensitivity to trajectory length: subsample long conversations to K=5, K=10, K=15 turns. Does the spectral radius stabilize?

- Deliverable: Table 4 draft — robustness summary. Key takeaway: are the findings stable or fragile?

## Week 7–8 — Write Paper A

- Paper A target: PROFES 2026 (16 pages LNCS, deadline Jul 23, 2026) or a workshop paper (4–6 pages) at EMNLP, NeurIPS, or EASE.

Paper A structure:

| Section | Pages | Content |
| --- | --- | --- |
| §1 Introduction | 1–1.5 | Drift in multi-turn LLM conversations; nobody has measured it with a state-space model; this paper does. |
| §2 Background | 1 | NSP definition (cite the NIER paper); spectral radius as drift diagnostic; feature extraction. |
| §3 Method | 1–1.5 | fit_nsp_text.py pipeline. Feature extraction → EM fit → spectral radius. Baselines (i.i.d., AR(1)). |
| §4 Datasets | 1 | LMSYS-Chat-1M, ShareGPT, MT-Bench. Sampling strategy, conversion, statistics. |
| §5 Results | 2–3 | RQ1: model comparison (Table 1). RQ2: turn-depth correlation (Figure 1). RQ3: NSP vs baselines (Table 3). Robustness (Table 4). |
| §6 Discussion | 1 | What the spectral-radius variation means for deployed LLM monitoring. Threats to validity. |
| §7 Related Work | 0.5–1 | Concept drift (Gama 2014), LLM evaluation (MT-Bench), conversational AI monitoring. |
| §8 Conclusion | 0.5 | Summary + pointer to Phase 2 detector work. |

## Week 9 — Submit Paper A + Phase 2 kickoff

- Submit Paper A. Advisor reviews final draft in Week 8. Student submits.

- Phase 2 planning meeting: decide Paper B venue, discuss annotation protocol, scope the detector.

# 5. Phase 2: Detect (Weeks 9–16)

Goal: build a lightweight drift detector on top of the fitted NSP, validate it against human annotations, add a change-point analysis, and write Paper B.

What Paper B adds beyond Paper A Paper A says: “we measured drift signatures and they vary.” Paper B says: “we built a detector that flags drifting conversations in real time, and human annotators agree with its flags.” That’s the difference between measurement and tooling — and it’s the difference between a short paper and a full paper.

## Week 9–10 — Build the drift scorer

Build score_drift.py — a companion to fit_nsp_text.py that takes the fitted NSP parameters and computes per-trajectory drift scores. The scorer implements Algorithm 2 from the NIER paper:

- Input: nsp_params.npz (from fit_nsp_text.py) + a new CSV of trajectories

- For each trajectory: run the Kalman forward pass using the fitted A, B, C, Q, Σ. At each turn k, compute the drift magnitude ‖X̂_k − X̂_0‖ (Euclidean distance of the filtered latent state from the initial state).

- Output: CSV with trajectory_id, turn_idx, drift_score, cumulative_drift, plus a per-trajectory summary (max drift, final drift, drift slope).

- Threshold: flag a trajectory as “drifted” if final drift > μ + 2σ of the training-set distribution. This is deliberately simple — the point is to see whether even a naive threshold correlates with human judgment.

- Deliverable: score_drift.py working end-to-end. Run on all three datasets. Save scored outputs.

## Week 10–11 — Human annotation study

The key contribution of Paper B is human validation. Without it, the detector is just a number — with it, the number means something.

- Sample 100 conversations from LMSYS-Chat-1M: 50 flagged as drifted by the detector, 50 not flagged. Randomize order.

- Recruit 3 annotators (fellow students, lab members, or Prolific workers — ~$50–100 total). Each annotator reads each conversation and answers two questions:

- (Q1) “Did the conversation drift away from the user’s original intent?” (Yes / No / Unclear)

- (Q2) “At which turn did drift become noticeable?” (turn number or N/A)

- Compute: inter-annotator agreement (Fleiss’ κ); precision/recall/F1 of the detector against majority-vote labels; Spearman ρ between detector’s drift score and annotators’ drift-onset turn.

- Deliverable: annotation spreadsheet, agreement metrics, precision/recall table.

## Week 12 — Change-point analysis

Add temporal structure to the drift score. Instead of just flagging whole conversations, detect where drift begins.

- CUSUM detector: apply a simple CUSUM (cumulative sum) chart to the per-turn drift_score sequence within each trajectory. The CUSUM flags a change-point when cumulative deviation exceeds a threshold h.

- Tune h on the annotated subset: set h to minimize |detected_turn − annotated_turn| on the 50 drifted conversations.

- Evaluate: mean absolute error between CUSUM-detected change-point and human-annotated drift-onset turn. Compare against two baselines: (a) always flag at the midpoint, (b) flag at the turn with maximum per-turn feature change.

- Deliverable: Figure 2 draft — example conversations showing drift score over turns with CUSUM-detected change-point vs. human annotation.

## Week 13 — Extended analysis for Paper B

- MT-Bench correlation: MT-Bench has human quality scores. Compute Spearman ρ between the NSP drift score and the human quality score. If drift → lower quality, the detector has practical value beyond drift detection.

- Error analysis: examine the false positives (detector says drifted, humans disagree) and false negatives (humans say drifted, detector misses). Categorize failure modes.

- Computational cost: report wall-clock time and memory for fit + score on each dataset. The detector needs to be fast enough for online use.

- Deliverable: correlation analysis, error taxonomy table, runtime table.

## Week 14–15 — Write Paper B

Paper B target: PROFES 2026 (if Paper A went to a workshop) or EASE 2027 / SANER 2027 / ICSME 2027 (full research paper, 14–16 pages).

| Section | Pages | Content |
| --- | --- | --- |
| §1 Introduction | 1.5 | Drift in deployed LLM conversations is undocumented and unmeasured. We present the first measurement + detection framework. |
| §2 Background | 1.5 | NSP definition; spectral radius; feature extraction; cite Paper A for the measurement results. |
| §3 Approach | 2 | Two-stage pipeline: fit_nsp_text.py for model fitting, score_drift.py for scoring. CUSUM change-point detector. Threshold calibration. |
| §4 Study design | 1.5 | Datasets (3). Annotation protocol (100 conversations, 3 annotators, Fleiss κ). Baselines (i.i.d., AR(1), midpoint, max-change). Metrics (precision, recall, F1, MAE for change-point). |
| §5 Results | 3–4 | RQ1: detector precision/recall vs human labels. RQ2: change-point accuracy vs human onset. RQ3: drift score vs MT-Bench quality. RQ4: cross-dataset generalization. Error analysis. Runtime. |
| §6 Discussion | 1.5 | When the detector works and when it doesn’t. Implications for LLM monitoring in production. Threats. |
| §7 Related work | 1 | Concept drift, LLM evaluation, conversational quality, runtime monitoring. |
| §8 Conclusion | 0.5 | Summary + pointer to the larger NSP research program. |

## Week 16 — Submit Paper B + wrap-up

- Submit Paper B. Advisor reviews final draft in Week 15.

- Archive: push all code, data-processing scripts, annotation data, and results to a GitHub repo. This becomes the artifact for both papers and the foundation for follow-on PhD work.

- Retrospective meeting: what worked, what didn’t, what the student wants to pursue next.

# 6. Week-by-week timeline

| Week | Focus | Deliverable | Student hours |
| --- | --- | --- | --- |
| 1 | Setup + data acquisition | 3 clean CSVs, environment working | 12–15 |
| 2 | Baseline NSP runs + synthetic validation | nsp_output/ for all 3 datasets; run_exp_a.py plot | 10–12 |
| 3 | Per-model and per-task splits | Table 1 (model families), Table 2 (task categories) | 12–15 |
| 4 | Turn-depth analysis | Figure 1 (spectral radius vs length), Spearman ρ | 8–10 |
| 5 | Baseline comparison (i.i.d., AR(1)) | Table 3 (log-likelihood comparison) | 10–12 |
| 6 | Robustness checks | Table 4 (sensitivity to D, features, K) | 8–10 |
| 7 | Write Paper A (draft) | Full draft circulated to advisor | 15–18 |
| 8 | Revise Paper A | Camera-ready draft | 10–12 |
| 9 | Submit Paper A + build score_drift.py | Paper A submitted; scorer working | 12–15 |
| 10 | Finish scorer + begin annotation study | Scored outputs for all datasets; annotation task deployed | 12–15 |
| 11 | Annotation study + analysis | Annotation spreadsheet; agreement metrics; P/R/F1 | 10–12 |
| 12 | Change-point analysis (CUSUM) | Figure 2 (drift curves + change-points); MAE | 10–12 |
| 13 | Extended analysis (MT-Bench correlation, error analysis, runtime) | Correlation table; error taxonomy; runtime table | 10–12 |
| 14 | Write Paper B (draft) | Full draft circulated to advisor | 15–18 |
| 15 | Revise Paper B | Camera-ready draft | 10–12 |
| 16 | Submit Paper B + archive + retrospective | Paper B submitted; GitHub repo archived | 8–10 |

Total student effort: ~175–210 hours across 16 weeks (≈11–13 hours/week). Compatible with a student taking one other course.

# 7. Venue options

## Paper A (short, Weeks 8–9)

| Venue | Format | Deadline | Fit |
| --- | --- | --- | --- |
| PROFES 2026 | 16 pages LNCS | Jul 23, 2026 | Strong — measurement + process improvement |
| EMNLP 2026 workshop | 4–8 pages | ~Sep 2026 | Strong — NLP + conversational AI |
| NeurIPS 2026 workshop (SoLaR, SafeGenAI) | 4 pages | ~Sep 2026 | Good — AI safety angle |
| EASE 2027 | 10 pages | ~Dec 2026 | Good — empirical SE |

## Paper B (full, Weeks 15–16)

| Venue | Format | Deadline | Fit |
| --- | --- | --- | --- |
| PROFES 2026 (if Paper A went to workshop) | 16 pages LNCS | Jul 23, 2026 | Strong |
| SANER 2027 | 10 pages IEEE | ~Oct 2026 | Strong — analysis + reengineering |
| ICSME 2027 | 10 pages IEEE | ~Apr 2027 | Strong — maintenance + evolution |
| EASE 2027 | 10 pages | ~Dec 2026 | Strong — empirical SE |
| MSR 2027 | 10 pages IEEE | ~Jan 2027 | Good — mining software repos angle |

# 8. Risks and mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| NSP spectral radius shows no variation across models | Low | A null result is publishable: “state-space models do not discriminate LLM drift signatures” scopes the theory. Paper A still contributes the first measurement. |
| NSP fits no better than i.i.d. baseline | Medium | Report it honestly. Identify which conversation types show signal vs. which don’t. The finding narrows the theory’s scope. |
| Human annotators disagree heavily (κ < 0.3) | Medium | Revise the annotation rubric. If still low, report it as a finding: “drift is subjectively ambiguous even for humans.” Switch Paper B’s evaluation to MT-Bench quality scores (no annotation needed). |
| CUSUM change-point doesn’t match human onset | Medium | Try Bayesian online change-point (Adams & MacKay) as a second detector. If both fail, the conclusion is “per-turn drift scoring works but temporal localization requires richer features.” |
| Student loses momentum mid-project | Medium | Paper A at Week 9 is a natural checkpoint. Even if Paper B doesn’t materialize, Paper A is a standalone deliverable. |
| Dataset access issues (LMSYS takedown) | Low | ShareGPT and MT-Bench are stable alternatives. Any two of the three datasets suffice. |

# 9. What the student owns at the end

- Two papers (one short, one full) with their name as first author

- A GitHub repository with all code, data-processing scripts, annotation data, and reproducible results

- Three reusable tools: fit_nsp_text.py (provided), score_drift.py (built in Phase 2), and the data-conversion scripts

- A research narrative that connects directly to the larger NSP/drift research program — natural entry point for a PhD if they want to continue

- Conference presentation experience (at least one talk or poster)